## Sheet4
Count of Defect ID | Column Labels
Row Labels | Closed | WIP | Grand Total
Bhushan |  | 3 | 3
Masroor |  | 3 | 3
NA | 7 |  | 7
Nikhil |  | 6 | 6
Nitesh |  | 5 | 5
Vidya |  | 4 | 4
Grand Total | 7 | 21 | 28

## Sheet1
Assigned To | Assigned to Username | Assinged On | Business Unit / Department | Defect ID | Defect Injection | Description | Detected By | Detected By User Name | Detected Date | Detected in Cycle | Priority | Sub-Function | Summary | IT Status | Owner | Comments
fgb2768 | Vishvas Kasurde | 2019-08-26 | 8/26/2019 3:30:15 PM | 601 | Defect Reference | Undrawn Commitment value is not saved | fgb2768 | Vishvas Kasurde | 2019-08-26 | UAT | 2-High | Nre/Modified facility | Undrawn Commitment value not saved | Closed | NA
fgb2768 | Vishvas Kasurde | 2019-08-26 | 8/26/2019 3:55:14 PM | 602 | Core Product Bug | Whenever any field related with repayment schedule modified then user should get an alert message before moving tonext screen. | fgb2768 | Vishvas Kasurde | 2019-08-26 | UAT | 2-High | Repayment module | Changes in the fields related with repayment schedule | WIP | Bhushan | If Bhushan will be able to build Save Repayment Module from his end then no need to implement this validation
fgb2768 | Vishvas Kasurde | 2019-08-26 | 8/26/2019 4:20:59 PM | 603 | Core Product Bug | CRWA, CAPITAL, APR, OPEX, COLLATERAL and point in time RAROC is blank facility ID N_Facility6592300963 | fgb2768 | Vishvas Kasurde | 2019-08-26 | UAT | 2-High | RAROC calculation | CRWA, CAPITAL, APR, OPEX, COLLATERAL and point in time RAROC is blank | WIP | Vidya | Masroor - APR Logic Pending. Please share the same. Other field logic implemented
fgb2768 | Vishvas Kasurde | 2019-08-26 | 8/26/2019 4:53:37 PM | 609 | Core Product Bug | Facility is for 2 years however getting yearly RAROC for 3rd year as well in lifetime RAROC screen N_Facility7251106483 | fgb2768 | Vishvas Kasurde | 2019-08-26 | UAT | 2-High | Lifetime RAROC calculation | Yearly RAROC in Lifetime RAROC screen | WIP | Bhushan
fgb2768 | Vishvas Kasurde | 2019-08-29 | 26-Aug-19 4:41:03 PM | 610 | Defect Reference | After generating the RAROC result, details on Pricing module is not getting saved once "Back" is selected even if saved.After generating the RAROC result, details on Pricing module is not getting saved once "Back" is selected even if saved. | FGB3179 | Anand Unadkat | 2019-08-26 | UAT | 2-High | Pricing Screen | Details not saved in the Pricing Module | Closed | NA
fgb2768 | Vishvas Kasurde | 2019-08-29 | 27-Aug-19 9:39:31 AM | 615 | Defect Reference | Sub-Industry not appearing correctly in the drop down option | FGB3179 | Anand Unadkat | 2019-08-27 | UAT | 2-High | Facility Details screen | Sub-Industry not appearing correctly in the drop down option | Closed | NA
fgb2768 | Vishvas Kasurde | 2019-08-29 | 27-Aug-19 9:54:28 AM | 616 | Defect Reference | Point in Time RAROC Result not available in some cases- Refer Deal Test AU11, ADNOC SCHOOLS-SAS AL NAKHL where ORR threshold checking was done. | FGB3179 | Anand Unadkat | 2019-08-27 | UAT | 2-High | RAROC Summary | Point in Time RAROC Result not available in some cases | WIP | Vidya
fgb2768 | Vishvas Kasurde | 2019-08-27 | 8/27/2019 12:46:05 PM | 619 | Core Product Bug | Validation is not checked for BOND type of collateral. System should ask bond issuer type and Bond issue rating. | FGB2768 | Vishvas Kasurde | 2019-08-27 | UAT | 2-High | Collateral Module | Mandatory field validation is not checked for BOND type of collateral | Closed | NA
fgb2768 | Vishvas Kasurde | 2019-08-27 | 8/27/2019 12:48:30 PM | 620 | Core Product Bug | Added bond collateral generating zero RAROC Facility reference no . N_Facility0238761295 | FGB2768 | Vishvas Kasurde | 2019-08-27 | UAT | 2-High | RAROC calculation | RAROC is zero after adding collateral details | WIP | Vidya | Masroor - Need Collateral Allocation Logic to fix this issue.
o14338 | Siddiqui Masroor Azar | 2019-08-27 | 27-Aug-19 2:54:51 PM | 623 | Core Product Bug | Interest Spread details should not be required field for unfunded facility | fgb3179 | Anand Unadkat | 2019-08-27 | UAT | 2-High | Facility Details | Interest Spread details should not be required field for unfunded facility | WIP | Nikhil | Nikhil - Change this field to Non - Mandatory Field on conditional basis. If user selected any Unfunded Product then user might enter value in this field. If user won't enter value then consider it as 0.
fgb2768 | Vishvas Kasurde | 2019-08-29 | 27-Aug-19 3:00:16 PM | 624 | Defect Reference | Fees income not getting reflected for unfunded facility Moreover RAROC result shown is also not correct. Refer the screenshot and Facility I'd | fgb3179 | Anand Unadkat | 2019-08-27 | UAT | 2-High | RAROC result | Fees income not getting reflected for unfunded facility | WIP | Masroor
o14338 | Siddiqui Masroor Azar | 2019-08-27 | 27-Aug-19 5:48:01 PM | 626 | Defect Reference | No need for additional details once facility status is selected as closure of facility | fgb3179 | Anand Unadkat | 2019-08-27 | UAT | 2-High | UI | No need for additional details once facility status is selected as closure of facility | WIP | Nitesh | Masroor - Please confirm below logic alos add the points if I have missed. 1) If user selected status of Facility = "Closuse of Facility" then he won't be able to move next page also other fields of that page gets disabled 2) This facility values should not consider in roll-up logic at customer and group level.
o14338 |  | 2019-08-28 | 28-Aug-19 10:41:38 AM | 630 | Defect Reference | Plesae make the mandatory field as conditional as discussed. For example, if facility is selected as "Funded" the mandatory field should be Interest Rate, Reference Rate etc. and if unfunded then mandatory field should be recurring fees and not the Interest Rate. | fgb3179 | Anand Unadkat | 2019-08-28 | UAT | 2-High | Pricing Screen | Required field in the Pricing Screen | WIP | Nikhil | Masroor - If user selected Funded Product then recurring Fee column is not mandatory? Please share the final logic of Mandatory / Non - Mandatory Columns.
o14338 |  | 2019-08-28 | 28-Aug-19 10:46:38 AM | 631 | Defect Reference | Rename the Cross Sell revenue and add mention amount in AED'000 in the Counterparty Details Screen | fgb3179 | Anand Unadkat | 2019-08-28 | UAT | 2-High | Counterparty Details Screen | Rename the Cross Sell revenue and add mention amount in AED'000 | WIP | Nikhil
o14338 | 29-Aug-19 8:03:01 PM | 2019-08-28 | 28-Aug-19 11:23:34 AM | 632 | Defect Reference | For 1 year deal, RAROC is not coming in YoY tab- refer the attachment. | fgb3179 | Anand Unadkat | 2019-08-28 | UAT | 2-High | RAROC Result | For 1 year deal, RAROC is not coming in YoY tab | WIP | Vidya
o14338 |  | 2019-08-28 | 28-Aug-19 11:34:12 AM | 636 | Defect Reference | Proposing new facility should not accept prior dates as facility start date | fgb3179 | Anand Unadkat | 2019-08-28 | UAT | 2-High | Facility Details | Proposing new facility should not accept prior dates | WIP | Nitesh
o14338 | Siddiqui Masroor Azar | 2019-08-28 | 28-Aug-19 2:01:02 PM | 637 | Product Feature | Please add customer name in the draft screen | fgb3179 | Anand Unadkat | 2019-08-28 | UAT | 2-High | Draft Screen | Customer Name at Draft Screen | WIP | Nitesh | Masroor - Need Clarification
o14338 |  | 2019-08-28 | 28-Aug-19 2:48:23 PM | 639 | Defect Reference | UAT user is able to proceed without viewing and saving the Repayment Schedule | fgb3179 | Anand Unadkat | 2019-08-28 | UAT | 2-High | Repayment Screen | UAT user is able to proceed without viewing and saving the Repayment Schedule | Closed | NA
o14338 | Siddiqui Masroor Azar | 2019-08-28 | 28-Aug-19 4:40:45 PM | 640 | Defect Reference | RAROC is not getting calculated frequently | fgb3179 | Anand Unadkat | 2019-08-28 | UAT | 2-High | RAROC Screen | RAROC is not getting calculated frequently | WIP | Masroor | Masroor- Need Scenarios to check Logic / Master data
o14338 |  | 2019-08-28 | 28-Aug-19 4:44:42 PM | 641 | Defect Reference | Repayment start date should not be greater than repayment end date- Validation Check Required | fgb3179 | Anand Unadkat | 2019-08-28 | UAT | 2-High | Repayment Module | Repayment start date should not be greater than repayment end date- Validation Check Required | WIP | Nikhil
o14338 |  | 2019-08-28 | 28-Aug-19 5:25:29 PM | 642 | Defect Reference | Outstanding should not be greater than Facility limit- Validation Check | fgb3179 | Anand Unadkat | 2019-08-28 | UAT | 2-High | Facility Details Screen | Outstanding should not be greater than Facility limit- Validation Check | Closed | NA
o14338 |  | 2019-08-28 | 28-Aug-19 5:30:12 PM | 643 | Defect Reference | Total should be shown at the bottom of Repayment Schedule view screen (Total Interest Charged & Total Principal Repaid) | fgb3179 | Anand Unadkat | 2019-08-28 | UAT | 2-High | Repayment Schedule | Total should be shown at the bottom of Repayment Schedule view screen (Total Interest Charged & Total Principal Repaid) | WIP | Bhushan
o14338 |  | 2019-08-28 | 28-Aug-19 5:55:02 PM | 648 | Defect Reference | Tranche condition not working in the repayment schedule. | fgb3179 | Anand Unadkat | 2019-08-28 | UAT | 2-High | Repayment Schedule | Tranche condition not working | WIP | Nikhil | Masroor - Need more details.
o14338 |  | 2019-08-28 | 28-Aug-19 6:33:35 PM | 649 | Defect Reference | Cap and Floor not considered in the Opex- Facility I'd-N_Facility7213460825 | fgb3179 | Anand Unadkat | 2019-08-28 | UAT | 2-High | RAROC calculation | Cap and Floor not considered in the Opex | WIP | Masroor
fgb2768 |  | 2019-08-29 | 8/29/2019 5:36:01 PM | 655 | Core Product Bug | Guarantor checkbox is not required | fgb2768 | Vishvas Kasurde | 2019-08-29 | UAT | 2-High | Facility details | Guarantor checkbox is not required | Closed | NA
fgb2768 |  | 2019-08-29 | 8/29/2019 5:38:50 PM | 656 | Core Product Bug | Outstanding/Notional Value should not be a mandatory field | fgb2768 | Vishvas Kasurde | 2019-08-29 | UAT | 2-High | Facility Details | Outstanding/Notional Value should not be a mandatory field | WIP | Nikhil | Nikhil - Make it as non mandatory field and while calculating repayment pass value as 0 to Bhushan's service. Note:- DO not save value to 0 in FCT_RAROC_PROJECTED_DTLS table.
fgb2768 | Vishvas Kasurde | 2019-08-29 | 8/29/2019 5:40:43 PM | 657 | Core Product Bug | Industry and country of risk should be auto populates based on counterparty UID. Currently user is selecting fromdropdown list. However user can modify these fields. | fgb2768 | Vishvas Kasurde | 2019-08-29 | UAT | 2-High | Facility Details | Industry and country of risk should be auto populates based on counterparty UID | WIP | Nitesh
fgb2768 | Vishvas Kasurde | 2019-08-29 | 8/29/2019 6:04:50 PM | 658 | Core Product Bug | ORR should come from GLCMS master | fgb2768 | Vishvas Kasurde | 2019-08-29 | UAT | 2-High | New Facility | ORR should come from GLCMS master | WIP | Nitesh